## Slide 1
Production of FCAL2 Modules
A. Somov
GlueX collaboration meeting, September 21, 2022
on behalf of the JEF and FCAL2 construction groups

## Slide 2: Introduction
- Project overview
- Fabrication of the FCAL2 insert modules
- Module design
- PbWO4 crystals
- Manpower
- Fabrication Schedule
- PMT and Active Base
- Construction schedule
https://halldweb.jlab.org/wiki/index.php/FCAL_Insert

## Slide 3: Calorimeter Upgrade
Forward Calorimeter
Install an array of 40 x 40 PbWO4 modules in the inner part of the FCAL
(replace lead glass modules)
- 2 cm x 2 cm x 20 cm PbWO4
- 4 cm x 4 cm x 45 cm lead glass
A factor of 4 better detector granularity
- significantly improve shower separation
Improves the energy and position resolutions by about a factor of 2
PbWO4 module

## Slide 4: Module Design
Nucl. Inst, Meth. A, 1013, 2021
PbWO4 crystal wrapped with the ESR reflective foil and light-tight Tedlar
PMT placed inside the mu-metal cylinder(s) and soft iron housing
3.5 mm long light guide (18.5 mm diameter) is glued to the PMT and coupled to
the crystal using a silicon cookie

## Slide 5: Parts for Module Assembly
Brazed strips
PMT with LG and
Silicon cookie
Wrapped PbWO4 module
PMT housing
mu-metal cylinder
50 m mu-metal foil

## Slide 6
Project Deadline and Schedule
End of the Spring 2023 run: March 15 2023
Start working on the FCAL upgrade in April (?)
Installation of the FCAL2 modules is scheduled on the middle of June 2023
- tentative installation schedule by Tim
Expected time to integrate the FCAL2 insert into the Hall D detector is about 10 months
All PbWO4 modules have to be fabricated and tested by June / July 2023
(including PMT dividers)
https://halldweb.jlab.org/wiki/images/0/0c/FCAL2_strawman_schedule.pdf

## Slide 7
Status of PbWO4 Crystals
SICCAS:
576 + 140 (installed on CCAL) = 716
- disassemble CCAL in January (or in March after the GlueX run)
CRYTUR:
Available: 722
Ordered: 105 (Physics DIV) Due date: December 2022
70 (Hall - D) Due date: May 2023
Total : 716 (SICCAS) + 897 (CRYTUR) = 1613
https://halldweb.jlab.org/wiki/index.php/CRYTUR
The inner part of the FCAL insert will be instrumented with the CRYTUR crystals

## Slide 8: Manpower for Module Fabrication
Jefferson Lab
Sasha, Arshak, Igal - crystal fabrication, preparation of parts
Chris Alan, Keith Bklackburn - brazing straps
Bobby Bunton - honing soft iron PMT housing
Tim / Mark - coordinating engineering efforts
JLab Detector support group
George Jackobs - preshaping ESR foils, fabricating modules
Mindy Leffel - wrapping crystals
GWU
Olga Cortes – testing PMTs, producing Silicon cookies, future divider testing
UNCW
future divider testing
Summer students !

## Slide 9: Summer Students
Tasks:
11 summer students at JLab from: GWU, UNCW, Lamar, and William & Marry
QA checks of SICCAS crystals taken from Hall C
Wrapping crystals
Cutting mu-metal, ESR, Tedlar, and Kapton foils
Gluing light guides
Module fabrication
Name | Affiliation |  | May | June |  | July |  | August |  | 
Jaden Sicotte | GWU |  |  |  |  |  |  |  |  | 
Dax Kay | GWU |  |  |  |  |  |  |  |  | 
Logan Earnest | GWU |  |  |  |  |  |  |  |  | 
Vadim Murakhovskiy | NOVA |  |  |  |  |  |  |  |  | 
Jared Curry | UNCW |  |  |  |  |  |  |  |  | 
Adam Sears | UNCW |  |  |  |  |  |  |  |  | 
Gavin Boilton | UNCW |  |  |  |  |  |  |  |  | 
Brandyn New | Lamar |  |  |  |  |  |  |  |  | 
Christopher Lowe | Lamar |  |  |  |  |  |  |  |  | 
Aaron Martinez | Lamar |  |  |  |  |  |  |  |  | 
Bradley Friedman | W&M |  |  |  |  |  |  |  |  | 

## Slide 10: Preparation of Parts
PMT
Light guide
Flange
Flange
Brass strap
Heat elements
Brazing brass assemblies
Wrapping crystals
Checking PMTs
Gluing Light guides
Wrapping ESR

## Slide 11: Parts for the FCAL Insert
receive by December
receive by the end of 2022
produce by the end of 2022

## Slide 12: Module Fabrication

## Slide 13: Module Fabrication
https://halldweb.jlab.org/wiki/index.php/Module_assembly

## Slide 14: Status of Fabrication
Total number of fabricated modules: 1221
Started module fabrication
in Feb 2022
Chart: Fabricated modules (per week)
| Feb 4 | Feb 11 | Feb 18 | Feb 25 | March 4 | March 11 | March 18 | March 25 | April 1 | April 8 | April 15 | April 22 | April 28 | May 6 | May 13 | May 20 | May 27 | June 3 | June 10 | June 17 | June 24 | July 1 | July 8 | July 15 | July 22 | July 29 | Aug 5 | Aug 12 | Aug 19 | Aug 26 | Sep 2
 | 14 | 27 | 30 | 19 | 23 | 29 | 36 | 29 | 36 | 25 | 20 | 30 | 25 | 28 | 38 | 22 | 0 | 26 | 8 | 52 | 89 | 148 | 107 | 91 | 112 | 8 | 57 | 30 | 51 | 12 | 7
Students in the Lab
https://halldweb.jlab.org/detectors/fcal2/module_fabrication/status/

## Slide 15: Fabricated Modules in EEL126
https://halldweb.jlab.org/detectors/fcal2/module_fabrication/status
5 shelves and 3 lockers

## Slide 16: Module Fabrication Schedule
December 31, 2022 1403 modules
Expect to fabricate all modules by the middle of June 2023
wrap 135 crystals (Mindy)
fabricate 182 modules
September 2022 1221 modules
January – April, 2023 1543 modules
disassemble CCAL
fabricate 140 modules
May – June, 2023 1613 modules
receive 70 Hall D CRYTUR crystals (May 2023)
(discuss if we can borrow crystals from EIC before we receive ours)

## Slide 17: PMT Active Base
Fernando
New design of the PMT active base
- no modifications of the divider (installed on the CCAL, linear performance)
- OPS –based amplifier with a separate power (+- 5V). The default gain is 3
- switches allow to by-pass the amplifier
- initially checked in the Lab; need to perform more tests (ongoing)
- need about 6 months to produce and test all dividers
- order in October / November
Signal
HV
low voltage

## Slide 18
Preparation for the FCAL2 Installation
see Tim’s talk (s)
Regular FCAL2 installation meetings organized by Tim
https://halldweb.jlab.org/wiki/index.php/FCAL_2_Installation_Meetings
- Coordinating with Fernando cable distributions
and connectors
- Installation procedures (module stacking, etc.)
Tasks for summer students:
- disassemble & sort out FCAL modules
- refurbish lead glass modules
- check PbWO modules in Hall D before installation
We will need at least 6 students during summer 2023

## Slide 19
Summary
We have 1438 PbWO crystals available in the lab
- expect to receive 105 crystals by the end of this year and 70 crystals by
May of 2023
We expect to fabricate all modules by the middle of June 2023
We have fabricated 1221 FCAL insert modules (about 77 % )
- a lot of work was done by students during summer
- 11 students were involved in the project
PMT active base prototypes are being tested in the lab. We expect to order them
in October / November
- active bases will be tested at JLab (GWU and UNCW)
We started working on the FCAL installation procedures
- Tim is organizing a biweekly installation meeting

## Slide 20
Backup Slides

## Slide 21: FCAL 2 Fabrication Labs
TEDF high bay
EEL 118

## Slide 22
Electronics
VXS crates
VXS Controllers
FADC 250
Trigger electronics (TI, SD, VTP, SSP, TD)
CAEN HV (A 7030 N) units and main frames
LV MPOD HV and signal cables
Main components have been purchased for
the FCAL insert (1600 modules)
VXS crates
Recently ordered: LEMO connectors
Need to order: LV cables, LV and HV (3 pin) connectors, electronics for the LMS (TDB)

## Slide 23
Tests of Fabricated Modules
3) Test PMT active bases (JLab, GWU, UNCW)
- check all active bases
Energy resolution of a single crystal
1 ) Use LEDs to check PMTs on fabricated modules
- have to check all modules
2 ) Use PS test setup to check some preselected modules

## Slide 24
Cable Distribution inside FCAL Dark Room
Fernando and Chris

## Slide 25
LV Cable distribution

## Slide 26
Crystal QA Tests
Visual inspection
Measurement of crystal dimensions
Measurement of light transmission
Measurement of light yield
Initial inspection of crystals at SICCAS by Wuhan group
- about 15% of crystals from the second batch rejected !
Crystal properties and testing procedures
Nucl.Instrum.Meth. A956 (2020) 163375
https://halldweb.jlab.org/wiki/index.php/PWO_Crystals

## Slide 27
Crystal Dimensions
Average crystal size (SICCAS):
20.56 mm
- consistent with crystals from
previous batches
The size of CRYTUR crystals is
20.5 mm
Crystal | Size |  |  | Size |  |  | Color | Scratch/Chip/Face | Bubble (%) /Layer | Blur | Chamfers | PS setup
246 | 20.501 | 20.555 | 20.502 | 20.514 | 20.565 | 20.506 | 0.5 |  |  |  | face small | 
247 | 20.533 | 20.558 | 20.511 | 20.519 | 20.557 | 20.527 |  |  | 30/0 |  |  | 
248 | 20.518 | 20.554 | 20.521 | 20.504 | 20.55 | 20.529 |  |  |  |  |  | 
249 | 20.53 | 20.562 | 20.512 | 20.529 | 20.565 | 20.521 |  |  |  |  |  | 
250 | 20.518 | 20.557 | 20.512 | 20.491 | 20.537 | 20.493 |  | 1/0/0 | 5/2 |  |  | 
251 | 20.514 | 20.553 | 20.51 | 20.502 | 20.548 | 20.496 |  |  |  |  |  | 
252 | 20.476 | 20.549 | 20.506 | 20.503 | 20.558 | 20.515 |  |  |  |  |  | 
253 | 20.509 | 20.549 | 20.507 | 20.513 | 20.55 | 20.512 |  | 0/0/1 | 30/1 | 1 |  | 
254 | 20.502 | 20.563 | 20.516 | 20.519 | 20.562 | 20.514 | 1 brown |  | 10/0 |  |  | 
Crystal quality chart:
https://halldweb.jlab.org/wiki/index.php/Second_Batch_(160_crystals)
Perform visual inspection and measure dimensions of all received crystals

## Slide 28
Visual Inspection
Check crystal color
Use laser pointer to observe cloudy regions
Check edge quality for scratches and chips
Brown
about 10 % crystals have some small discoloration signs

## Slide 29
Measured transmission of 30 SICCAS crystals from the second batch:
- selected crystal with some discoloration signs after optical inspection
- correlation between the crystal color and transmission
Light Transmission Measurement
Setup in Carl Zorn’s lab

## Slide 30
Light Transmission Measurement
colored crystals
10 colored crystals
in the test
Measured crystals meet our specs
Good consistency between our results and measurements at SICCAS

## Slide 31: PMT Active Base
Consider to use an active PMT base designed for the NPS (Hall C)
- the base consists of the divider and an amplifier (original gain of 24)
The Active Base was installed on CCAL and used during the PrimEx run in spring 2019
- observed non-linear performance
- linearity was improved after reducing gain
- non–linear performance verified using bench tests
https://halldweb.jlab.org/JEF/meetings/feb_11_2021/fcal_amp_lin.pdf
New Active PMT Base for PbWO4 (Popov, H. Mkrtchyan, presentation at IEEE, Nov 2012)
CCAL was testes in GlueX runs at high luminosity
- studied detector rates
- an amplifier will the small gain ( between 3 and 6) will be needed for inner FCAL layers

## Slide 32
Amplifier Gain (A amp / A HP )
10 GeV
2.5 GeV
Relatively stable gain for amplitudes between 0.5 V and 1.6 V
Non linearity on the level of 10 % below 0.5 V
PMT Active Base

## Slide 33
PMT Active Base
Several meetings with Fernando and Vlad. May consider to use
alternative solutions:
- use on-board amplifier, provide additional power to the amplifier
(decouple power for divider and amplifier), use one extra cable to each PCB)
- use external amplifiers for modules in inner layers (place inside dark room ?)
Several improvements by Vlad Popov in order to improve performance
- tests are ongoing
Test of PMT dividers can be performed outside JLab
- several universities are interested to participate: Regina, GWU, UNCW

## Slide 34
Crystal Transmittance

## Slide 35: Light Yield Setup
New setup at TEDF (similar to NPS lab)
- crate with readout electronics
- CODA running on local PC
Trigger
LaBr(Ce) scint
PWO
Na-22 β+ and gamma source
- two 0.511 MeV photons. One used
for the trigger

## Slide 36: Light Yield Setup