## Sheet1
Task List of FCAL2 installation
March 22, 2023 - May 15, 2024
Tentative plan, Sasha & Arshak
This document contains major milestons of the FCAL2 detector installation
Will be handled by the JEF and Hall D physics
| DSG |  | Detector support Group
| FE |  | Fast Electronics group (Chris C., Fernando B.)
STEP 1 : Disassemble FCAL
Task | Start | End | Duration | Group | Comments
Remove TOF, prepare FCAL upstream platform | 2023-03-22 |  |  | Tim’s group
Label bad lead glass (LG) modules and disconnect detector cables, bundle cables, etc. | 2023-03-29 | 2023-04-28 | 4 weeks | Mark, Malte, Chris S
Prepare to remove FCAL LG modules (remove cable bundles, trays, remove dark room, place LG cables on support stands, etc.) | 2023-05-01 | 2023-05-21 | 3 weeks | Tim’s group
Remove FCAL modules | 2023-05-22 | 2023-06-26 | 4 min per module 5 weeks | DSG group, YerPhI, Sasha, Arshak, Igal, students, Mark, Malte | HDList (Tim, Sasha, Arshak, Mark, Malte)
STEP 2: Prepare for detector installation
Remove/modify liftable frame, assemble new FCAL frame, install cooling blocks, etc | 2023-06-26 | 2023-07-25 | 4 weeks | Tim's group
STEP 3: Detector Installation
Install LG and PbWO modules (install dividers on stacked PbWO modules) | 2023-07-26 | 2023-10-18 | 7 min per module 12 weeks | YerPhI, Sasha, Arshak, students | HDList, Tim, Sasha, Arshak, req. "crane support "
Prepare and install dark room cable trays, etc (ready for cabling) | 10/18/2023 | 11/8/2023 | 3 weeks | Tim's group
Install LMS | 2023-11-10 | 2023-11-25 | 2 weeks | Arshak, Sasha, Tim's group
STEP 4: Install Racks and Crates
Install 4 racks | 2023-10-18 | 2023-10-25 | 1 week | Tim's group
Install VXS crates, HV crates, LV crate (and electronics modules) | 2023-10-26 | 2023-11-08 | 2 weeks | Chris S., FE group, Sasha, Arshak
Install optical links | 2023-10-26 | 2023-11-08 | 1 week | FE group
Install trigger modules (in trigger crates) | 2023-10-26 | 2023-11-26 | 4 weeks | FE group, Sasha, Arshak
Install Ethernet switche (if needed) | 2023-10-27 | 2023-11-03 | 1 week | Sergey (IT division)
STEP 5: Install Cables
Install LG cables | 11/9/2023 | 12/22/2023 | 1.5 months | Chris S., Mark, Malte
Install PbWO cables (HV, LV, signal) connect to dividers | 11/9/2023 | 2/14/2024 | 18 min per module 3 months | FE/DSG group, Chris S. Sasha, Arshak
STEP 6: Final test of the FCAL 2
Integrate FCAL2 inser into the GlueX slow control (HV, scalers, environment, etc) |  | 2/15/2024 |  | Hovanes
Integrate FCAL2 insert into trigger and DAQ | 2/15/2024 | 5/1/2024 | 10 weeks | Sasha, Arshak
Test the FCAL2 detector | 2/15/2024 | 5/15/2024 | 12 weeks | Sasha, Arshak, Mark, Malte
Work performed in parallel with the detector installation
Refurbish FCAL lead glass modules
Visually inspect uninstalled LG modules | 2023-05-22 | 2023-07-30 | 5 weeks | DSG group, Sasha, Arshak, Mark, Malte, Igal, students | HDList (Sasha, Arshak, Mark, Malte)
Repair LG modules (if needed) | 2023-05-22 | 2023-09-29 | 19 weeks | DSG group, Sasha, Arshak, Mark, Malte, Igal, students
Replace LG PMTs | 2023-05-22 | 2023-09-29 | 19 weeks | Mark, Malte, Chris S.
Replace / fix PMT dividers | 2023-05-22 | 2023-09-29 | 19 weeks | Mark, Malte, Chris S.
Prepare PbWO detector for installation (1596 modules)
Prepare cables (install connectors, etc) | 2023-05-01 | 2023-07-03 | 10 weeks | Chris S., FE group, DSG group | HDList (Tim, Sasha, Arshak)
Label cables | 2023-05-15 | 2023-08-18 | 14 weeks | DSG group, Chris S., Sasha, Arshak, students
Connect signal cables (inside dark box) to patch panel | 2023-06-15 | 2023-08-15 | 10 weeks | Sasha, Arshak, Chris S., students
Prepare cables for installation (bundle, ring) | 2023-05-15 | 2023-08-15 | 14 weeks | Sasha, Arshak, Chris S., students
Check dividers | 2023-05-15 | 2023-07-26 | 10 weeks | Sasha, Arshak, DSG, Chris S., students
Move modules to the hall, fix module assemblies (if needed) | 2023-05-15 | 2023-08-18 | 14 weeks | Sasha, Arshak, students
Check modules with LED | 2023-05-15 | 2023-08-18 | 14 weeks | Sasha, Arshak, Igal, Chris S., DSG, students
LMS system
Finalize design of the LMS for the PbWO insert |  | 2023-03-01 |  | Arshak, Sasha, Tim's group | HDList (Tim, Arshak, Sasha)
Prepare all parts | 2023-03-02 | 2023-06-01 | 12 weeks | Arshak, Sasha, Tim's group
Test LMS in the lab | 2023-05-02 | 2023-06-02 | 4 weeks | Arshak, Sasha, students
Refurbish LMS for the FCAL LG region | 2023-05-22 | 2023-09-01 | 14 weeks | Arshal, Sasha, Tim's group