## Sheet1
Resfac
Availability of summer students | [7 empty] | 2022-05-27 |  |  | 2022-06-21
Name | Affiliation |  | Duration of stay |  | JLab regestration | TA | Lodging | May | June |  | July |  | August
Jaden Sicotte | GWU |  | 2.5 months | 5/15 - 7/1 | done | done | on site
Dax Kay | GWU |  | 1.5 months | 5/11 - 6/22 | done | done | on site
Vadim Murakhovskiy | NOVA |  | 2 months (up to 3 months) | 5/16 - 8/15 | done | done | on site
Jared Curry | UNCW |  | 2 months (up to 2.5 months) | 6/1 - 7/31 | done | done | on site
Adam Sears | UNCW |  | 2 months (up to 2.5 months) | 6/1 - 7/31 | done | done | on site
Gavin Bolton | UNCW |  | 2 months (up to 2.5 months) | 6/1 - 7/31 | done | done | on site
Brandyn New | Lamar |  | 2 months (up to 2.5 months) | 6/6 - 8/12 | done | done | on site
Christopher Lowe | Lamar |  | 2 months (up to 2.5 months) | 6/10 -8/19 | done | done | coming today
Aaron Martinez | Lamar |  | 2 months (up to 2.5 months) | 6/21 - 8/18 | done | submitter
Logan Earnest | GWU |  | 1 month | 7/19-8/20 | done | in preparation
[8 empty] | 3 | 7 | 8 | 7 | 7 | 4 | 1
Total |  |  | 72 weeks
Assume 1 months = 4 weeks
Projects for students:
Task (for student) |  | Estimated time (weeks) | Number of students work in parallel
Wrapping crystals |  | 43 (8 per day) | 2
Glying and wrapping |  | 17 (30 min module) | 1
light guides
Cutting foils |  | 4 | 2
Module fabrication |  | 30 - 40 min per module
(TBD)
Testing fabricated |  | 10 (15 min per module) | 2
modules using LED
Quality check of crystals |  | 2 (30 min per crystal)
(visual inspection, dimensions)
100 NPS crystals
80 Hall D crystals
Testing fabricated |  | Loading test stand
modules using PS |  | data analysis
setup
Total |  | 76 weeks
Preparation to the
PrimEx run
Fix broken TAGH
counters
Build spare TAGH
counters
Check CCAL
Software projects
CCAL geometry
MC simulation