## Slide 1: Current status and plan on PWO crystal production
Hui YUAN
Shanghai Institute of Ceramics, CAS
2022.01.10

## Slide 2
3rd batch(10kg) and 4th batch(10kg) received and used during the past 2 months.
Much less than expected.
The reasons of Instable production:
Epidemic situation
Government order
3. Internal management
Current status of PbO quality checking and results

## Slide 3
3rd batch PbO: good cx(most qualified),
nearly no bad cx.
4th batch PbO: few good cx, return to previous
bad situation
The factory has the ability to produce good PbO, but it seems they don’t work smoothly during the past months.
Current status of PbO quality checking and results

## Slide 4
Projected crystal production
The preliminary plan is to provide the 3rd batch delivery of about 100 pcs crystals by the end of March.
We will cooperate the factory to improve the yield of the PbO as high as possible to catch up with the delayed production.