## Sheet1
List of parts for PWO module fabrication ( January 2020)
Item | Procurement Status | Availability by 3/2020 | Comments
PMT housing | In production | 20 | Productuon rate 100/month | Tim
Produced at CMU, Annealed at Jlab
350 um mu-metal schileding cylinder | Ordered | 20 | Order for 1600 modules (?) | Tim
50 um mu-metal foil | Ordered | 20 | Order for 1600 modules (?) | Tim
Kapton | Available (?) |  |  | Tim
Light Guides | To be ordered | 20 | Order for 500 modules | Tim
Production rate: fast
RTV615 | Available | yes |  | Sasha
ESR | Ordere for 1600 modules | yes |  | Sasha
Tedlar | Available | yes |  | Sasha
Flanges | Quotes for (500 and 1600) | 20 |  | Sasha
Brass strips | Order for 70 modules | 20 |  | Sasha/Tim
Waiting for quotes
Screws | Available | yes |  | Sasha
PMT tension plate (G10) | Available for about 100 modules | 20 |  | Tim
Have to order
Tape