## Sheet1
| 2021 | [7 empty] | 2022 | [11 empty] | 2023
| May | June | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov
Crystals
- available at JLab | 2021 May: installed by October: 360
- next batch
PMTs
- available at JLab | 2021 May: 500
- ordered | 2021 Aug: 1000
- installed on CCAL (142)
Module production
- pre-production | 2021 May: 50 modules
- production | 2021 July: 1 technician (100 modules per month), 1100 modules
- students involved | 2022 June: 500 modules
Module testing
- beam tests | 2021 Oct: PrimEx/SRC/CT; 2022 May: CPP (?)
- cosmic tests | bar: 2022 Jan to 2022 Dec
PMT electronics
- prototype (by Fernando) | bar: 2021 May to 2021 June
- bench tests | bar: 2021 July to 2021 Oct
- beam tests (SRC / CT exp) | bar: 2021 Nov to 2021 Dec
- pre-production | bar: 2022 Jan to 2022 Feb
- production | bar: 2022 Mar to 2022 June
- test | bar: 2022 May to 2022 Sep
LMS system
- design | bar: 2022 June to 2022 Sep
- build | bar: 2022 Oct to 2023 Feb
Installation in the Hall | bar: 2023 Apr to 2023 Sep
- uncable FCAL
- disassamble FCAL
- upgrade FCAL frame
- install modules
- install crates and elec.
- install signal and HV cables