## rebaseline_5_steps
Activity | Name | B_Start | B_End | Total | Procurement | Labor | PRCRMN | PURMAT | PURLAB | SRSTAF | SCIENT | COMSCI | MECENG | MECDES | MECTEC | ELCENG | ELCDES | ELCTEC | UNSTAF | SKLTRD | STUDNT | VISITR | TRAVEL | CONTRB | EVMS | % | % new | Calc start | Calc finish | Actual start | Actual finish | Expected start | Expected finish
2541152 | Algorithm_Development_for_DC_FADC125_FY13 | 2013-09-03 | 2013-09-30 | 1707.11 | 0 | 1707.11 | 0 | 0 | 0 | 0 | 0.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S | 20 | 35 | 2013-11-01 | 2014-08-20 | 2013-11-01
____step | __Initial_algorithm_development |  |  | 20 | [21 empty] | 100
____step | __Coordination_of_the_code_implementation |  |  | 15 | [21 empty] | 0 | 100
____step | __Testing_of_initail_algorithm |  |  | 20 | [21 empty] | 0
____step | __Algorithm_adjustment |  |  | 15 | [21 empty] | 0
____step | __Coordination_of_the_adjusted_code_implementation |  |  | 15 | [21 empty] | 0
____step | __Testing_of_adjusted_algorithm |  |  | 15 | [21 empty] | 0
2541152a | Algorithm_Development_for_DC_FADC125_FY14 | 2013-10-01 | 2014-08-20 | 18693.7 | 0 | 18693.7 | 0 | 0 | 0 | 0 | 6.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S | 20 | 35 | 2013-11-01 | 2014-08-20 | 2013-11-01
____step | __Initial_algorithm_development |  |  | 20 | [21 empty] | 100
____step | __Coordination_of_the_code_implementation |  |  | 15 | [21 empty] | 0 | 100
____step | __Testing_of_initail_algorithm |  |  | 20 | [21 empty] | 0
____step | __Algorithm_adjustment |  |  | 15 | [21 empty] | 0
____step | __Coordination_of_the_adjusted_code_implementation |  |  | 15 | [21 empty] | 0
____step | __Testing_of_adjusted_algorithm |  |  | 15 | [21 empty] | 0
2541154 | Code_Deployment_and_Full_Readout_Tests_FADC125 | 2014-04-07 | 2014-09-30 | 17486.42 | 0 | 17486.42 | 0 | 0 | 0 | 0 | 6.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S | 0 |  | 2014-04-07 | 2014-09-30
____step | __Code conversion to FPGA |  |  | 20 | [21 empty] | 0
____step | __Test algorithm data |  |  | 20 | [21 empty] | 0
____step | __Deploy code |  |  | 30 | [21 empty] | 0
____step | __Readout tests |  |  | 30 | [21 empty] | 0