## Counter Info
Final State of Light-Guide/ Scintillator
Scintillator Counter # | Why it was removed from TAGH | Problems Found | What was repaired |  | Date Taken Out | Date Reinstalled
113 | Loose scintillator | Scintillator broken in two towards base | scintillator replaced, plastic endpiece added |  | 2019-06-10 | 2019-07-02
116 | Loose scintillator | Scintillator broken in two towards base, 1 disconnected wire at the circuit board | scintillator replaced, wire reattached, plastic endpiece added |  | 2019-06-10 | 2019-07-02
119 | Loose scintillator | Scintillator no longer securely attached to light guide | scintillator reattached, plastic endpiece added |  | 2019-07-02 | 2019-07-10
125 | Loose scintillator | Scintillator no longer securely attached to light guide, 1 disconnected wire at the circuit board | scintillator reattached, wire reattached, plastic endpiece added |  | 2019-06-10 | 2019-07-02
144 | Loose scintillator | Scintillator no longer securely attached to light guide | scintillator reattached, plastic endpiece added |  | 2019-06-10 | 2019-07-02
161 | Loose scintillator | Scintillator no longer securely attached to light guide | scintillator reattached, plastic endpiece added |  | 2019-06-10 | 2019-07-02
187 | Loose scintillator | Scintillator no longer securely attached to light guide | scintillator reattached, plastic endpiece added |  | 2019-07-02 | 2019-07-10
196 | Loose scintillator | Scintillator no longer securely attached to light guide, scratches on scintillator around base | scintillator replaced, plastic endpiece added |  | 2019-07-02 | 2019-07-10
212 | Loose scintillator | Scintillator no longer securely attached to light guide | scintillator reattached, plastic endpiece added |  | 2019-07-02 | 2019-07-10
228 | Loose scintillator | Scintillator no longer securely attached to light guide |  |  | 2019-07-02 | 2019-07-10
138 | Loose scintillator |  |  |  | 2019-07-10
184 | Loose scintillator |  |  |  | 2019-07-10
83 | Loose scintillator |  |  |  | 2019-07-10
92 | Loose scintillator |  |  |  | 2019-07-10
229 | Loose scintillator |  |  |  | 2019-07-10
230 | Loose scintillator |  |  |  | 2019-07-10
84 | Loose scintillator |  |  |  | 2019-07-10
126 | Loose scintillator |  |  |  | 2019-07-10
123 | Loose scintillator |  |  |  | 2019-07-10

## Counters to be Repaired
7/2/2019 Examination of Scintillator Counters in TAGH reveled the following have loose scintillators | Some Counters must also be relabeled
98
101
110
125
170
231