## Sheet1
Activity ID | Activity Name | Start | Finish | Elec tech (mw) | Mech tech (mw) | Mech Des (mw) | Mech Eng (mw) | Budgeted Labor Units | Budgeted Labor Cost | Budgeted Material Cost | Budgeted Nonlabor Cost | Budgeted Total Cost | Total Float | New start | New finish | New Elec tech (mw) | New Mech tech (mw) | New Mech Des (mw) | New Mech Eng (mw) | New Scient (mw)
1.5.5.2 TARGET |  | 2011-04-05 08:00 | 2013-01-22 16:00 |  |  |  |  | 29 | 62371 | 202177 | 0 | 264548 | 52.8
1552001 | Prepare Procurements/Fabrication Packages 2011 (TARGET) | 2011-10-03 08:00 | 2012-01-03 16:00 |  |  | 4 | 4 | 8 | 17774 | 0 | 0 | 17774 | 52.8 | 2011-04-01 | 2011-09-30
1552002 | Evaluate Procuements 2012 (TARGET) | 2012-01-30 08:00 | 2012-03-30 16:00 |  |  | 1 | 2 | 3 | 7078 | 0 | 0 | 7078 | 52.8 | 2012-03-10 | 2012-05-10
1552003 | FY12 Engineering Support for Assembly (TARGET) | 2012-01-05 08:00 | 2012-07-10 16:00 |  |  | 12 | 6 | 18 | 37519 | 0 | 0 | 37519 | 52.8
1552005 | Proc Gas Handling Sys (TARGET) | 2012-01-05 08:00 | 2012-07-10 16:00 |  |  |  |  | 0 | 0 | 26371 | 0 | 26371 | 52.8
1552005a | Develop gas handling system | [12 empty] | 2011-04-01 | 2011-09-01 |  | 6 | 6 | 8
1552010 | Proc Controls (TARGET) | 2011-04-05 08:00 | 2011-10-06 16:00 |  |  |  |  | 0 | 0 | 57137 | 0 | 57137 | 90 | 2012-03-05 | 2012-08-05
1552015 | Fab Isolation Vac Pumping Sys (TARGET) | 2012-01-05 08:00 | 2012-07-10 16:00 |  |  |  |  | 0 | 0 | 25272 | 0 | 25272 | 52.8 | 2012-06-05 | 2012-09-30
1552020 | Fab Outer Vac/Scattering Chamb (TARGET) | 2012-01-05 08:00 | 2012-07-10 16:00 |  |  |  |  | 0 | 0 | 9889 | 0 | 9889 | 52.8
1552020a | Fab Outer Vac/Scattering Chamb labor (TARGET) | [12 empty] | 2012-01-05 | 2012-07-10 |  | 6 |  | 1
1552025 | Fab Target Cells (TARGET) | 2012-01-05 08:00 | 2012-07-10 16:00 |  |  |  |  | 0 | 0 | 10988 | 0 | 10988 | 52.8
1552025a | Fab Target Cells labor | [12 empty] | 2012-01-05 | 2012-07-10 |  | 6
1552027 | Burst test target cell | [12 empty] | 2012-03-05 | 2012-06-05 |  | 4 |  | 2
1552030 | Proc Liquid Helium refrigerator (TARGET) | 2011-05-05 08:00 | 2011-11-07 16:00 |  |  |  |  | 0 | 0 | 55000 | 0 | 18679 | 85.6 | 2011-10-01 | 2012-02-02
1552031 | Develop cryo system design | [12 empty] | 2011-06-01 | 2011-09-30 |  | 6 | 6 | 8
1552032 | Procure heat xchngr and cryo hardware | [8 empty] | 15000 |  |  |  | 2012-01-05 | 2012-04-01
1552035 | Fab Positioning/Mounting Sys (TARGET) | 2012-01-05 08:00 | 2012-07-10 16:00 |  |  |  |  | 0 | 0 | 53840 | 0 | 53840 | 52.8
1552040 | Assemble Target (TARGET) | 2012-07-11 08:00 | 2013-01-22 16:00 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 52.8 |  |  |  | 9 |  | 2
1552045 | Program controls | [12 empty] | 2012-10-01 | 2013-01-22 |  |  |  | 3 | 4
[5 empty] | 0 | 17 | 12 | [9 empty] | 37 | 12 | 24 | 4
modified field |  |  | MW | 37 | 29 | 36 | 4 |  |  | 253497
new activity |  |  |  | tech | des | eng | sci
modified activity